## DVPR Template
Senior Capstone Design
Project: | IoT Smart Building Sensors |  | Primary Author: | Jared Gradin, Tristan Clawson
Team: | Team TBD |  | Date: | 2019-10-24
Design Validation Plan & Results (DVP&R)
Requirement | Test | Test Subject | Target Date | Result | Recommendation
Writes sensor data to JSON | Pushbutton event triggers program that writes to JSON | Basic Prototype w/ Raspberry Pi | 2019-11-01
Send JSON data over internet to server | Test depends on the capabilities of AWS Cloud, but right now send the JSON file to the server in some way | Raspberry Pi set up to interface with AWS Cloud | 2019-11-15
System shall not overheat past 80 degrees Celsius | Measure temperature under operation | Full working prototype | 2020-03-15
95/100 events successfully log on server | Send 100 events, measure how many get logged successfully on server | Full working prototype | 2020-03-15
No crashes/freezes after 72hrs use | Run device 72 hours (weekend), check back to see if still operational | Full working prototype | 2020-03-15
Pi encrypts JSON information when sending to server | Use wireshark to detect packets incoming and determine | Basic working prototype | 2019-12-01
Pi records and encrypts event | Use wireshark to detect that packets encrypted. Check Pi for local copy of event. | Full working prototype | 2020-03-15
Pi sends JSON to stub/demo server | Check server for expected event | Full working prototype | 2020-03-15
Stub/demo server decrypts JSON and displays | Compare decrypted JSON with original stored on the Pi. | Full working prototype | 2020-03-15