## Schedule
Capstone Project Schedule Template - Fall-Spring
|  |  | Project: | Iot Security
|  |  | Last Updated: | 2019-10-09
|  |  | Year | 2018 | [16 empty] | 2019
|  |  | Month | Sept |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec |  |  |  | Jan |  |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May
| Task Description | Duration | Assigned | 2018-09-03 | 2018-09-10 | 2018-09-17 | 2018-09-24 | 2018-10-01 | 2018-10-08 | 2018-10-15 | 2018-10-22 | 2018-10-29 | 2018-11-05 | 2018-11-12 | 2018-11-19 | 2018-11-26 | 2018-12-03 | 2018-12-10 | 2018-12-17 | 2018-12-24 | 2018-12-31 | 2019-01-07 | 2019-01-14 | 2019-01-21 | 2019-01-28 | 2019-02-04 | 2019-02-11 | 2019-02-18 | 2019-02-25 | 2019-03-04 | 2019-03-11 | 2019-03-18 | 2019-03-25 | 2019-04-01 | 2019-04-08 | 2019-04-15 | 2019-04-22 | 2019-04-29 | 2019-05-06 | 2019-05-13 | 2019-05-20 | 2019-05-27
| Get Raspberry Pi | 1
| Set up Pi with AWS Greengrass | 1
| Logbook & Portfolio to Dr. Bolden | 1
| Set up Pi with AWS Greengrass | 1
| Learn Python & Supporting tools | 2
| Send .json message | 1
| Set up server for testing Pi hub | 1
| Set up encryption for messages | 2
| Get another microcontroller for lief nodes | 2
| Program lief nodes to work with Pi | 2
| Develop database for storing .json messages | 2
| Deliverables due | 1
| Explore other sensor types w/ same hardware | 3
| Implement wireless communication | 2
| Create server for Pi to interface with | 2
| Program GUI for server for ease of use | 3
Build working model
Finish Documentation & Prepare for presentation